## Sheet1
Schedule |  |  | usr stories <-- Include when we developped these
| Task | In Charge | Status | Comments???
Week 1 (1/18-1/24)
Initial Prepatory Work
| 1. Set up version control using GitHub | CC & BY & YY
| 2. Set up shared drive for files using Google Drive | CC & BY & YY
| 3. Set up Android Studio and install Parse | CC & BY & YY
| 4. Make Schedule and Split Tasks | CC & BY & YY
Verify Functionality of Parse
| 1. Create Parse Account | CC & BY & YY
| 2. Set up Android Studio to push data to Parse | CC & BY & YY
| 3. Create our shared Parse User field for our project | CC & BY & YY
| 4. Verify data has been pushed to Parse | CC & BY & YY
Create Login Page: Part I
| 1. Create Login screen frontend. | MN & LL
| 2. Push and store data in frontend fields. | MN & LL
| 3. Create usernames and password field. | MN & LL
| 4. Push usernames and passwords to Parse database. | MN & LL
| 5. Pull correct username and password from Parse. | MN & LL
| 6. Verify usernames and passwords are stored correctly. | MN & LL
| 7. Merge with repository and push code. | MN & LL
Week 2 (1/25-1/31)
Create and overall scheme of how we want pages to progress.
| 1. List of pages/activities we need to represent all events. | YY
| 2. A page for each activity (login, create account, events list, create events, manage events, profile view, logout). | YY
| 3. Draft a paper prototype of how each page would look like. | YY
| 4. Link each page progress. | YY
| 5. Post on shared folder. | YY
Create Frontend of Event Page: Part I
| 1. Create an activity page that hooks to Parse. | CC & BY
| 2. Figure out what buttons we need. | CC & BY
| 3. Draft what we want the page to look like. | CC & BY
4. List fields for Events page
Create Login Page: Part II
| 1. Set up ability for user to create accounts. | MN & LL
| 2. Allow user to login with previously created account. | MN & LL
| 3. Verify usernames are unique and passwords aren't simple. | MN & LL
| 4. Verify non-unique usernames can't be created. | MN & LL
| 5. Merge with repository and push code. | MN & LL
Week 3 (2/1-2/7) - Note: Midterm Next Week (Work will be shortened)
Plan Baseline
| 1. List all functions customer's want to see. | ALL
| 2. Figure out which functions are required. | ALL
| 3. Draw a prototype for what our baseline product will look like. | ALL
Scaffolding for Create Account Page
| 1. List data fields we want for the initial Create Accounts Page | MN & LL
| 2. Decide what buttons we want on the page. | MN & LL
| 3. Draw a paper prototype for what we want the design to look like. | MN & LL
Week 4 (2/8-2/14)
Create Main Page
| 1. Plan the frontend view of the Events page. | CC & YY
| 2. Set background of Events list page. | CC & YY
| 3. Create navigation (back, home) for the page. | CC & YY
| 4. List fields for Events page | CC & YY
Create New Account Page
| 1. Create the UI with all relevant data fields. | MN & LL
| 2. Hook up each data field to a column in Parse. | MN & LL
| 3. Create corresponding columns in Parse website. | MN & LL
| 4. Create a mock account to verify data is pushed correctly. | MN & LL
| 5. Pull data from app to verify data pulled correctly. | MN & LL
| 6. Link the Log in page with the Create Account page. | MN & LL
| 7. Link the Create Account page back to the Log In page. | MN & LL
Week 5 (2/15 - 2/21)
Create UI for Create Events Page
| 1. List fields we need for Create Events (title, location, time, etc.) | YY
| 2. Plan layout of navigation and clickable buttons. | YY
| 3. Create a paper draft of the UI of Create Events | YY
| 4. Implement UI of page in Android Studio. | YY
Event List Page
| 1. Hook up Login Page and Create Account Page to Event List. | MN & LL
| 2. Hook up log out button to return to login page when "logging out". | MN & LL
| 3. Pull Events list for unique user account from parse. | MN & LL
| 4. After creating a mock event, make sure to add self user to event. | MN & LL
| 5. Sort events in chronological order. | MN & LL
| 6. Link the Event List page back to Log In page. | MN & LL
Week 6 (2/22 - 2/28)
Create UI for Create Events Page
| 1. List fields we need for Create Events (title, location, time, etc.) | YY
| 2. Plan layout of navigation and clickable buttons. | YY
| 3. Create a paper draft of the UI of Create Events | YY
| 4. Implement UI of page in Android Studio. | YY
Create Events Page
| 1. List data fields we need for event. | MN & LL
| 2. Create UI with a field for each piece of data. | MN & LL
| 3. Push data to Parse along with unique user ID. | MN & LL
| 4. Have a mock account join the event. | MN & LL
| 5. Allow host to view the attendee/mock account. | MN & LL
6. Link the Create Events page back to Events List page.
Week 7 (2/29-3/6)
Edit Profile Page
| 1. Draft the UI that displays all profile information. | YY
| 2. Place the "Save Changes" and "Cancel" buttons at bottom for edit profile. | YY
| 3. Push and override changes on Parse | YY
| 4. Make sure new changed profile is pulled from Parse. | YY
Join Events Page
| 1. Create the UI that views all events possible to join. | MN & LL
| 2. Order events chronologically. | MN & LL
| 3. Create corresponding columns in Parse website. | MN & LL
| 4. Create a mock event on Parse and pull it to the Join Events page. | MN & LL
| 5. Join event and make sure user is registered for event. | MN & LL
| 6. Link the Join Events page back to Events List back via back button. | MN & LL
Week 8 (3/7-3/11)
Brainstorm tests to run
| 1. List an overall view of different scenarios of integration testing. | YY
| 2. List the purpose of each integration testing (designed to test "x") | YY
| 3. Create pseudocode for the test. | YY
Implement Integration Tests
| 1. Write basic integration test that check each activity is connected. | MN & LL
| 2. Write different scenarios of integration tests. | MN & LL
| 3. Run integration tests. | MN & LL
| 4. Schedule time for fixes of each integration test. | MN & LL
Fix Remaining Bugs
| 1. Order remaining bugs in order of priority and difficulty. | MN & LL
| 2. Fix all critical, low difficulty bugs first. | MN & LL
| 3. Fix all low difficulty bugs next. | MN & LL
| 4. Fix all critical, medium difficulty bugs last if time permits. | MN & LL
| 5. Document all remaining bugs and plans to fix given more time. | MN & LL